## COEM_Package_20200302
No | Package | Type | Project | ComponentName | TaskID | ItemName | Database | ItemRevision | Task Jira | TaskGroup | Tester | LOC | LOC Complete | Estimation hour | Actual hour | Status | Planned Start | Planned End | Start | End | C0 | C1 | MCDC | Reason
1 | 1 | PSW | HIDEN | HIDEN | HIDEN | HIDEN | HIDEN | HIDEN | N/A |  | duong.nguyen | 113 | 113 | #REF! |  | Ongoing | 2020-03-02 | 2020-03-04 | 2020-03-02
2 | 1 | PSW | HIDEN | HIDEN | HIDEN | HIDEN | HIDEN | HIDEN | N/A |  | loc.do-phu | 459 | 459 | #REF! |  | Ongoing | 2020-03-02 | 2020-03-04 | 2020-03-02 |  |  |  |  | Tool collect 148 LOC, but the real is 459
3 | 1 | PSW | HIDEN | HIDEN | HIDEN | HIDEN | HIDEN | HIDEN | N/A |  | duong.nguyen | 291 | 291 | #REF! |  | Ongoing | 2020-03-02 | 2020-03-04 | 2020-03-02
4 | 1 | PSW | HIDEN | HIDEN | HIDEN | HIDEN | HIDEN | HIDEN | N/A |  | chung.ly | 254 | 254 | #REF! |  | Ongoing | 2020-03-02 | 2020-03-03 | 2020-03-02
5 | 1 | ASW | HIDEN | HIDEN | HIDEN | HIDEN | HIDEN | HIDEN | N/A |  | thanh.nguyen-kim | 19 | 19 | #REF! |  | Ongoing | 2020-03-02 | 2020-03-04 | 2020-03-02
6 | 2 | PSW | HIDEN | HIDEN | HIDEN | HIDEN | HIDEN | HIDEN | N/A |  | thanh.nguyen-kim | 478 | 478 | #REF! |  | Ongoing | 2020-03-02 | 2020-03-04 | 2020-03-02
7 | 2 | PSW | HIDEN | HIDEN | HIDEN | HIDEN | HIDEN | HIDEN | N/A |  | loc.do-phu | 286 | 286 | #REF! |  | Ongoing | 2020-03-02 | 2020-03-04 | 2020-03-02
8 | 2 | PSW | HIDEN | HIDEN | HIDEN | HIDEN | HIDEN | HIDEN | N/A |  | chung.ly | 110 | 110 | #REF! |  | Ongoing | 2020-03-02 | 2020-03-04 | 2020-03-02
9 | 3 | PSW | HIDEN | HIDEN | HIDEN | HIDEN | HIDEN | HIDEN |  |  |  | 251 |  |  |  | N/A | 2020-03-02 | 2020-03-04
10 | 3 | PSW | HIDEN | HIDEN | HIDEN | HIDEN | HIDEN | HIDEN |  |  |  | 101 |  |  |  | N/A | 2020-03-02 | 2020-03-04
11 | 3 | PSW | HIDEN | HIDEN | HIDEN | HIDEN | HIDEN | HIDEN |  |  |  | 90 |  |  |  | N/A | 2020-03-02 | 2020-03-04
12 | 3 | PSW | HIDEN | HIDEN | HIDEN | HIDEN | HIDEN | HIDEN |  |  |  | 101 |  |  |  | N/A | 2020-03-02 | 2020-03-04
Table KPI ASW
No | Tester | Total Loc Assigned | Total LOC Complete | Total Day | KPI/days | Status (%)
1 | hieu.nguyen-trung | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2 | hau.nguyen-tai | 0 | 0 | 0 | #DIV/0! | #DIV/0!
3 | bang.nguyen-duy | 0 | 0 | 0 | #DIV/0! | #DIV/0!
4 | dac.luu-cong | 0 | 0 | 0 | #DIV/0! | #DIV/0!
5 | duong.nguyen | 0 | 0 | 0 | #DIV/0! | #DIV/0!
6 | loc.do-phu | 0 | 0 | 0 | #DIV/0! | #DIV/0!
7 | thanh.nguyen-kim | 19 | 0 | 0 | #DIV/0! | 0%
8 | chung.ly | 0 | 0 | 0 | #DIV/0! | #DIV/0!
Table KPI PSW
No | Tester | Total Loc Assigned | Total LOC Complete | Total Day | KPI/days | Status (%)
1 | hieu.nguyen-trung | 0 | 0 | 0 | #DIV/0! | #DIV/0!
2 | hau.nguyen-tai | 0 | 0 | 0 | #DIV/0! | #DIV/0!
3 | bang.nguyen-duy | 0 | 0 | 0 | #DIV/0! | #DIV/0!
4 | dac.luu-cong | 0 | 0 | 0 | #DIV/0! | #DIV/0!
5 | duong.nguyen | 404 | 0 | 0 | #DIV/0! | 0%
6 | loc.do-phu | 745 | 0 | 0 | #DIV/0! | 0%
7 | thanh.nguyen-kim | 478 | 200 | 0 | #DIV/0! | 41.84%
8 | chung.ly | 364 | 0 | 0 | #DIV/0! | 0%

## Table
KPI Table
No\Type | ASW | PSW
1 | 130 | 450
Table Type of Testing
No | Type | Tool | Detail Output
1 | ASW | ATT | 1. Test Design (.xls) 2. Plot File (.plt) 3. ATT project 4. Coverage Log
2 | PSW | Cantata | 1. TPA file (.tpa) 2. test report (.html) 3. test report (.xml) 4. test summary (.html) 5. File Coverage Fail Reason (.xls)
Table Tester
No | Member
1 | hieu.nguyen-trung
2 | hau.nguyen-tai
3 | bang.nguyen-duy
4 | dac.luu-cong
5 | duong.nguyen
6 | loc.do-phu
7 | thanh.nguyen-kim
8 | chung.ly
Status Table
No | Status
1 | N/A
2 | Ongoing
3 | Ready for review
4 | Ready for PLC

## Template_Weekly_Report
Date | 2020-02-03
Total Days | 20
1. Completed ELOCs of the team from the beginning of Month (Mar) till Now:
|  | # | Types | Assigned ELOCs | Completed ELOCs | Status (%) (Completed/Assigned)
|  | 1 | PSW | ??? | ??? | ???
|  | 2 | ASW | ??? | ??? | ???
2. Completed ELOCs of each member from the beginning of Month (Mar) till Now:
|  | # | External Name | PSW ELOCs | ASW ELOCs
|  | 1 | hieu.nguyen-trung | ??? | ???
|  | 2 | duong.nguyen-tuan | ??? | ???
3. Risks/ Pending Issues:
|  | # | Risks/ Issues
1
2
4. Found Defects/ OPLs in Month (Mar):
|  | # | Defects / OPLs
1
2
5. Leave Plan (Mar):
|  | # | External Name | Num of Day | Detail
|  | 1 | hieu.nguyen-trung | ??? | ???
|  | 2 | duong.nguyen-tuan | ??? | ???
Note:
Productivity of each Member per Day
PSW: 450 ELOCs
ASW: 150 ELOCs
Total Productivity per Month
PSW: 450x4x20 = 36,000 ELOCs
ASW: 130x4x20 = 10,400 ELOCs