## Slide 1: Ban Vien Monthly Report
May - 2020

## Slide 2: Agenda
Summary
Detail report
  Productivity, ELOC
  On Time Delivery
  Defects raised
Resource Allocation
Staffing Plan
Problems & Issues

## Slide 3: Summary
Overall status: Green
Headline:
  Resources status:
Project Performance | May.2020
Completed/Delivered Tasks | 101
Completed/Delivered Effort (MD) | 99646 ELOCs
Resource Allocation in Month May.2020 (MD) | -
Productivity Rate by Effort | 117 %
New found defects in May.2020 | 1
New found defects (cumulative from Jan.2020) | -
Number of valid detected defects per spent average Man-Month per year. | 0.1
Key Performance Indicator | May.2020
Overall Project status | 
ELOC deliverables | 
Delivery On Time | 
Defect raised by team | 
Month | Project | HC | Note
Apr-20 | JOEM | 1 | 
 | COEM | 9 | 
 | Grand Total | 10 | 
May-20 | JOEM | 2 | 
 | COEM | 8 | 
 | Grand Total | 10 | 

## Slide 4: Deliverables COEM (1)
Project | Types | Assigned task (ELOC) | Assigned date | Target date | Delivered task (ELOC) | Delivered date | Remain (ELOC) | % Completion
206370_BYD_ESP9.3_New_Hybrid_MS15.1_BSS18 | PSW | 3939 | 4/28/2020 | 5/14/2020 | 3939 | 5/14/2020 | 0 | 100
216916_FAW_E115_L3_ESPhev_APB(CBi)_BL60 | ASW | 84 | 5/4/2020 | 5/8/2020 | 84 | 5/7/2020 | 0 | 100
217437_FAW_C229_BL43 | PSW | 648 | 5/6/2020 | 5/11/2020 | 648 | 5/11/2020 | 0 | 100
228771_SAIC EP22 X1 & IP31E w/o_DA ESPHevX BSS04_SP01 | PSW | 455 | 4/28/2020 | 5/5/2020 | 455 | 5/5/2020 | 0 | 100
235199_SAIC_EP21_MCE_ESP9.3HevX | PSW | 817 | 5/15/2020 | 5/20/2020 | 817 | 5/18/2020 | 0 | 100
237281_GAC_A76_CarbonESP9.3CP_BL04 | PSW | 42 | 5/13/2020 | 5/15/2020 | 42 | 5/13/2020 | 0 | 100
238493_GAC_A36_CarbonESP9.3CP_BL04 | PSW | 88 | 5/13/2020 | 5/15/2020 | 88 | 5/13/2020 | 0 | 100
BAIC_C62X_RC_APA_BL01 | PSW | 1911 | 5/6/2020 | 5/8/2020 | 1911 | 5/8/2020 | 0 | 100
BAIC_N60_iBooster | PSW | 1133 | 5/18/2020 | 5/22/2020 | 1133 | 5/20/2020 | 0 | 100
BJEV_N60_2WD_4WD | ASW | 21 | 5/19/2020 | 5/26/2020 | 21 | NA | 0 | 100
BJEV_N60_2WD_4WD | PSW | 5700 | 5/11/2020 | 5/26/2020 | 5700 | NA | 0 | 100
BYD_IPB_SW_Mainstream_BL05 | PSW | 220 | 5/15/2020 | 5/20/2020 | 220 | 5/18/2020 | 0 | 100
CNMS_179148_Carbon_ESP_BL07_SPRINT12 | PSW | 1680 | 5/20/2020 | 6/3/2020 | 1680 | NA | 0 | 100
CNMS_226315_HevX_RPA_BL03SP03 | ASW | 242 | 5/4/2020 | 5/8/2020 | 242 | 5/7/2020 | 0 | 100
CNMS_226528_IB2_RPA | ASW | 20 | 5/11/2020 | 5/12/2020 | 20 | 5/12/2020 | 0 | 100
Carbon RPA | PSW | 1588 | 5/4/2020 | 5/8/2020 | 1588 | 5/7/2020 | 0 | 100
DFN_ESP_Gen9.3_534_238307_BS03SP03 | ASW | 45 | 5/4/2020 | 5/6/2020 | 45 | 5/5/2020 | 0 | 100
DFN_ESP_Gen9.3_534_238307_BS03SP03 | PSW | 2540 | 5/7/2020 | 5/12/2020 | 2540 | 5/12/2020 | 0 | 100
EC_245950_NIO_ESX_ESPHevX_DTC | PSW | 342 | 5/7/2020 | 5/12/2020 | 342 | 5/12/2020 | 0 | 100
EC_245950_NIO_ESX_ESPHevX_DTC_BSS04_SP02 | PSW | 63 | 5/13/2020 | 5/14/2020 | 63 | 5/14/2020 | 0 | 100
Total effort was completed by customer/OEM in May 2020
No | Total
PSW | 49441
ASW | 549

## Slide 5: Deliverables COEM (2)
Project | Types | Assigned task (ELOC) | Assigned date | Target date | Delivered task (ELOC) | Delivered date | Remain (ELOC) | % Completion
FAW_E115_ESPhev_BSL60 | ASW | 97 | 5/11/2020 | 5/19/2020 | 97 | 5/18/2020 | 0 | 100
FAW_E115_ESPhev_BSS60 | PSW | 902 | 5/14/2020 | 5/19/2020 | 902 | 5/19/2020 | 0 | 100
FAW_TypeC2_BSL33_Security | PSW | 466 | 5/19/2020 | 5/26/2020 | 466 | NA | 0 | 100
GAC_220680_Carbon_A18_ESPHevx_FPA/RPA_BL04 | PSW | 1309 | 4/28/2020 | 5/7/2020 | 1309 | 5/7/2020 | 0 | 100
GAC_220680_Carbon_A18_ESPHevx_FPA/RPA_BL05 | PSW | 63 | 5/8/2020 | 5/11/2020 | 63 | 5/12/2020 | 0 | 100
GAC_239741_Carbon_A12 4WD ESPHevx FPA/RPA_BL02 | PSW | 857 | 5/15/2020 | 5/20/2020 | 857 | 5/18/2020 | 0 | 100
GAC_Carbon_RPA_ESPHevx_Mainpath_BL04 | PSW | 1555 | 5/6/2020 | 5/11/2020 | 1555 | 5/12/2020 | 0 | 100
GAC_Carbon_RPA_ESPHevx_Mainpath_BL05 | PSW | 746 | 5/6/2020 | 5/7/2020 | 746 | 5/7/2020 | 0 | 100
GAC_Carbon_Stream_ESPCP_BL05 | PSW | 6027 | 4/29/2020 | 5/13/2020 | 6027 | 5/11/2020 | 0 | 100
GEEA2.0_ESP9.3_CMP_BL07 | PSW | 1087 | 5/19/2020 | 5/20/2020 | 0 | 5/20/2020 | 1087 | 0
GEELY_BX11_ESPHEVX_BL06_SP02 | PSW | 284 | 5/20/2020 | 5/22/2020 | 284 | NA | 0 | 100
GEELY_FE-3AH_CB_CSIS241976_BSS03 | PSW | 928 | 4/28/2020 | 5/5/2020 | 928 | 5/5/2020 | 0 | 100
GEELY_FS11_ESP9.3HD_BSS05_SP05 | PSW | 86 | 5/18/2020 | 5/27/2020 | 86 | NA | 0 | 100
GEELY_SS11ESP9.3CP_BL02_SP04 | PSW | 957 | 5/18/2020 | 5/20/2020 | 957 | 5/20/2020 | 0 | 100
GWM AB30 7DCT | PSW | 3952 | 5/14/2020 | 5/19/2020 | 3952 | 5/19/2020 | 0 | 100
GWM CHB027 RC3 ESP9.3 | PSW | 82 | 5/4/2020 | 5/6/2020 | 82 | 5/5/2020 | 0 | 100
GWM_AB30_7DCT_BSS08 | PSW | 267 | 5/15/2020 | 5/20/2020 | 267 | 5/18/2020 | 0 | 100
MC_237270_GAC_A55CP_Carbon_ESP_BL02 | PSW | 272 | 5/8/2020 | 5/11/2020 | 272 | 5/12/2020 | 0 | 100
MC_239446_Geely_FE6AB_ESP9.3HD_BB81527_BL04 | PSW | 86 | 5/6/2020 | 5/8/2020 | 86 | 5/8/2020 | 0 | 100
MC_239507_SGMW_CN210S_PHEV_ESP9.3CPi_BSS02_SP2 | ASW | 40 | 5/13/2020 | 5/15/2020 | 40 | 5/13/2020 | 0 | 100
Total effort was completed by customer/OEM in May 2020

## Slide 6: Deliverables COEM (3)
Project | Types | Assigned task (ELOC) | Assigned date | Target date | Delivered task (ELOC) | Delivered date | Remain (ELOC) | % Completion
MC_239507_SGMW_CN210S_PHEV_ESP9.3CPi_BSS02_SP2 | PSW | 159 | 5/11/2020 | 5/13/2020 | 159 | 5/13/2020 | 0 | 100
MC_239507_SGMW_CN210S_PHEV_ESP9.3CPi_BSS03_SP1 | PSW | 615 | 4/29/2020 | 5/6/2020 | 615 | 5/6/2020 | 0 | 100
RC_242264_SOKON_S513EVR_ESP9.3 | PSW | 107 | 5/8/2020 | 5/14/2020 | 107 | 5/13/2020 | 0 | 100
RTN_MOTO][RT750-J] | PSW | 163 | 5/11/2020 | 5/15/2020 | 163 | 5/15/2020 | 0 | 100
SAIC ZS12MCE withDA ESP9.3 BSS03SP01 | PSW | 167 | 5/6/2020 | 5/8/2020 | 167 | 5/8/2020 | 0 | 100
SGMW CN202M 208T CPi ACC 242139 BB81871 | PSW | 1567 | 5/18/2020 | 5/27/2020 | 1567 | NA | 0 | 100
XE431RC ABS10.3ME | PSW | 5571 | 5/4/2020 | 5/15/2020 | 5571 | 5/13/2020 | 0 | 100
Total effort was completed by customer/OEM in May 2020

## Slide 7: Deliverables COEM (4)
Project | Types | Assigned task (ELOC) | Assigned date | Target date | Delivered task (ELOC) | Delivered date | Remain (ELOC) | % Completion
231839_DearCC_IC321_ESP9.3_BSS02_CAN_MATRIX_VARTABLE | PSW | 180 | 4/20/2020 | 4/24/2020 | 180 | 4/24/2020 | 0 | 100
233324_JAC_P843_ESP9.3_BSS05 | PSW | 1673 | 4/20/2020 | 4/28/2020 | 1673 | 4/28/2020 | 0 | 100
242899_GAC_A39_ESP9.3CPHD_RC4_BL011 | PSW | 1329 | 4/20/2020 | 4/29/2020 | 1329 | 4/27/2020 | 0 | 100
AB30IB2 | PSW | 2084 | 4/20/2020 | 4/30/2020 | 2084 | 4/29/2020 | 0 | 100
AB30IB3 | PSW | 29 | 4/21/2020 | 4/24/2020 | 29 | 4/24/2020 | 0 | 100
AB30IB4 | PSW | 276 | 4/21/2020 | 4/24/2020 | 276 | 4/24/2020 | 0 | 100
AB30IB5 | PSW | 150 | 4/21/2020 | 4/24/2020 | 150 | 4/24/2020 | 0 | 100
Adapt_236234_SMART_VDDM_ESPHevX_BSS02_E2_SP3 | PSW | 60 | 4/20/2020 | 4/24/2020 | 60 | 4/24/2020 | 0 | 100
Adapt_236246_SMART_BBM_Ibooster_E2_SP3 | PSW | 1721 | 4/20/2020 | 4/24/2020 | 1721 | 4/24/2020 | 0 | 100
BYD_Carbon_Mainstream_BL02spr02 | PSW | 2067 | 4/13/2020 | 4/29/2020 | 2067 | 4/29/2020 | 0 | 100
BYD_IPB_SW_Mainstream_BL05_Defect | PSW | 803 | 4/20/2020 | 4/21/2020 | 803 | 4/21/2020 | 0 | 100
BYD_IPB_SW_Mainstream_BL05_SP10 | PSW | 919 | 4/20/2020 | 4/21/2020 | 919 | 4/21/2020 | 0 | 100
BYD_IPB_SW_Mainstream_BL05_SP11 | ASW | 173 | 4/17/2020 | 4/23/2020 | 173 | 4/23/2020 | 0 | 100
BYD_IPB_SW_Mainstream_BL05_SP11 | PSW | 293 | 4/20/2020 | 4/21/2020 | 293 | 4/21/2020 | 0 | 100
BYD_IPB_SW_Mainstream_BL05_SP12 | ASW | 30 | 4/21/2020 | 4/29/2020 | 30 | 4/29/2020 | 0 | 100
BYD_IPB_SW_Mainstream_BL05_SP12 | PSW | 676 | 4/20/2020 | 4/29/2020 | 676 | 4/27/2020 | 0 | 100
CNMS_226528_IB2_RPA_BL03SP06 | ASW | 70 | 4/24/2020 | 4/28/2020 | 70 | 4/28/2020 | 0 | 100
CNMS_226528_IB2_RPA_BL03SP07 | ASW | 110 | 4/24/2020 | 4/28/2020 | 110 | 4/28/2020 | 0 | 100
FAW_E111_ESPhev | PSW | 1330 | 4/20/2020 | 4/23/2020 | 1330 | 4/22/2020 | 0 | 100
FAW_E115_ESPhev | PSW | 590 | 4/20/2020 | 4/29/2020 | 590 | 4/27/2020 | 0 | 100
Total effort was completed by customer/OEM in Apr 2020
No | Total
PSW | 28458
ASW | 792

## Slide 8: Deliverables COEM (5)
Project | Types | Assigned task (ELOC) | Assigned date | Target date | Delivered task (ELOC) | Delivered date | Remain (ELOC) | % Completion
BYD_IPB_SW_Mainstream_BL05_SP10 | PSW | 1226 | 4/1/2020 | 4/21/2020 | 1226 | 4/21/2020 | 0 | 100
BYD_IPB_SW_Mainstream_BL05_SP11 | ASW | 173 | 4/17/2020 | 4/23/2020 | 173 | 4/23/2020 | 0 | 100
BYD_IPB_SW_Mainstream_BL05_SP11 | PSW | 873 | 4/20/2020 | 4/21/2020 | 873 | 4/21/2020 | 0 | 100
BYD_IPB_SW_Mainstream_BL05_SP12 | ASW | 30 | 4/21/2020 | 4/29/2020 | 30 | 4/29/2020 | 0 | 100
BYD_IPB_SW_Mainstream_BL05_SP12 | PSW | 676 | 4/20/2020 | 4/29/2020 | 676 | 4/27/2020 | 0 | 100
CNMS_226528_IB2_RPA_BL03SP06 | ASW | 70 | 4/24/2020 | 4/28/2020 | 70 | 4/28/2020 | 0 | 100
CNMS_226528_IB2_RPA_BL03SP07 | ASW | 110 | 4/24/2020 | 4/28/2020 | 110 | 4/28/2020 | 0 | 100
EC_245950_NIO_ESX_ESPHevX_DTC_BSS01_SP01 | PSW | 2260 | 4/14/2020 | 4/17/2020 | 2260 | 4/17/2020 | 0 | 100
FAW D090 High/Low G6 ECR | PSW | 78 | 4/16/2020 | 4/17/2020 | 78 | 4/17/2020 | 0 | 100
FAW_E111_ESPhev | PSW | 1330 | 4/20/2020 | 4/23/2020 | 1330 | 4/22/2020 | 0 | 100
FAW_E115_ESPhev | PSW | 590 | 4/20/2020 | 4/29/2020 | 590 | 4/27/2020 | 0 | 100
GAC_212111_Carbon_A12_iB2_FPA/RPA_BL02 | PSW | 263 | 4/20/2020 | 4/22/2020 | 263 | 4/22/2020 | 0 | 100
GAC_219651_Carbon_A18_iB2_FPA/RPA_BL04 | PSW | 165 | 4/20/2020 | 4/22/2020 | 165 | 4/22/2020 | 0 | 100
GAC_220680_Carbon_A18_ESPHevx_FPA/RPA_BL04_TestExecution | PSW | 235 | 4/20/2020 | 4/22/2020 | 235 | 4/22/2020 | 0 | 100
GAC_Carbon_RPA_iBooster_Mainpath_BL04 | ASW | 121 | 4/24/2020 | 4/28/2020 | 121 | 4/28/2020 | 0 | 100
GAC_Carbon_Stream_ESPCP_BL05 | ASW | 229 | 4/24/2020 | 4/29/2020 | 229 | 4/29/2020 | 0 | 100
GAC_Carbon_Stream_ESPCP_BL05 | PSW | 2578 | 4/20/2020 | 4/29/2020 | 2578 | 4/27/2020 | 0 | 100
GAC_Common_Task_Record_Sprint07 | PSW | 235 | 4/16/2020 | 4/17/2020 | 235 | 4/17/2020 | 0 | 100
GEELY_BX11_ESP9.3HD_BL06_SP02 | ASW | 50 | 4/17/2020 | 4/21/2020 | 50 | 4/21/2020 | 0 | 100
GEELY_BX11_ESP9.3HD_BL06_SP02 | PSW | 200 | 4/17/2020 | 4/20/2020 | 200 | 4/20/2020 | 0 | 100
Total effort was completed by customer/OEM in Apr 2020

## Slide 9: Deliverables JOEM (1)
Project | Types | Assigned task (ELOC) | Assigned date | Target date | Delivered task (ELOC) | Delivered date | Remain (ELOC) | % Completion
HONDA_CMP_BL11sp02_snapshot05 | ASW | 1719.9 | 5/11/2020 | 5/26/2020 | 1355.9 | NA | 364 | 78.83597884
HONDA_CMP_BL11sp02_snapshot05 | PSW | 5148 | 5/11/2020 | 5/26/2020 | 5148 | NA | 0 | 100
HONDA_iB2_1401_BL09_Sprint02 | ASW | 494 | 5/6/2020 | 5/8/2020 | 494 | 5/8/2020 | 0 | 100
HONDA_iB2_1401_BL09_Sprint02 | PSW | 1080 | 5/6/2020 | 5/8/2020 | 1080 | 5/8/2020 | 0 | 100
TOY_847B_MPT_Release1 | ASW | 299 | 4/25/2020 | 5/7/2020 | 299 | 5/7/2020 | 0 | 100
TOY_847B_MPT_Release1 | PSW | 3852.225 | 4/25/2020 | 5/7/2020 | 3852.225 | 5/7/2020 | 0 | 100
Total effort was completed by customer/OEM in May 2020
No | Total
PSW | 9666.225
ASW | 2148.9

## Slide 10: Deliverables
Metric | Actual Value | Note
Delivered ELOC (LOC) | ASW: 1341 PSW: 77899 | 
Productivity (ELOC/Month) | 485.5 | KPI: 450 ELOCs/PSW, 130 ELOCs/ASW
Productivity Rate by ELOC (%) | 107.9% | KPI: 450 ELOCs/PSW, 130 ELOCs/ASW
Total ELOC, Productivity (ELOC/MD) and Productivity Rate in May 2020 for COEM
Metric | Actual Value | Note
Delivered ELOC (LOC) | ASW: 2148.9 PSW: 9666.225 | 
Productivity (ELOC/Month) | 570.2 | KPI: 450 ELOCs/PSW, 130 ELOCs/ASW
Productivity Rate by ELOC (%) | 126.7% | KPI: 450 ELOCs/PSW, 130 ELOCs/ASW
Total ELOC, Productivity (ELOC/MD) and Productivity Rate in May 2020 for JOEM

## Slide 11: On Time Delivery
OTDQ: No of On time tasks delivered/ Total No of tasks delivered * 100
 | Total delivered tasks | OTD task | % Delivery on-time
JOEM | 4 | 4 | 100%
COEM | 74 | 71 | 95.9%
Overall | 78 | 75 | 96.2%
Chart to show OTD over months

## Slide 12: Valid Defect over effort
Project | Defect | ID/Description
XE431RC ABS10.3ME | 1 | Defect 1481021
Grand Total | 1 | -
Total valid defect | Avg HC | Valid Defect over Effort
1 | 10 | 1/10 = 0.4

## Slide 13: Resource allocation
No | Resource name | Project | Start Date | End Date | Number of leave days | Notes
1 | Nguyen Trung Hieu | COEM | 21-Apr | 20-May | 0 | 
2 | Nguyen Tai Hau | COEM | 21-Apr | 20-May | 0 | 
3 | Nguyen Duy Bang | COEM | 21-Apr | 20-May | 0 | 
4 | Luu Cong Dac | COEM, JOEM | 21-Apr | 20-May | 0 | 
5 | Nguyen Tuan Duong | COEM | 21-Apr | 20-May | 0 | 
6 | Do Phu Loc | COEM | 21-Apr | 20-May | 1 | 15-Apr
7 | Nguyen Kim Thanh | COEM | 21-Apr | 20-May | 3 | 21,22,23-Apr
8 | Ly Chung | COEM | 21-Apr | 20-May | 1 | 3-Apr
9 | Do Anh Huy | COEM, JOEM | 21-Apr | 20-May | 0 | 
10 | Nguyen Thanh Phuong | COEM | 21-Apr | 20-May | 0 | 
 | Apr.2020 | May.2020 | Note
JOEM | 0 | 2 | 
COEM | 10 | 8 | 
Total | 10 | 10 | 
Staffing plan
Resource allocation in month