## COEM_Package_20200302
No | Package | Type | Project | ComponentName | TaskID | ItemName | Type of Comment | BB | Database | ItemRevision | Owner Contact | Task Jira | TaskGroup | Tester | PeerReviewer | Status Review | ELOC Assigned | ELOC Recheck With Tool | LOC Complete | Estimation base TOOL | Actual hour | Status | Planned Start | Planned End | Start | End | Status Result | C0 | C1 | MCDC | Reason | Remark
1 | 20200302 | PSW |  |  |  |  | Auto | [5 empty] | T01 | duong.nguyen | hieu.nguyen-trung | Yes | 113 | 113 | 113 | 3 | 4 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-02 | 2020-03-03 | OK | 100 | 100 | 100
2 | 20200302 | PSW |  |  |  |  | Auto | [5 empty] | T01 | loc.do-phu | hieu.nguyen-trung | Yes | 148 | 357 | 357 | 10 | 6 | Ready for review | 2020-03-03 | 2020-03-04 | 2020-03-02 | 2020-03-02 | OK | 100 | 100 | 100
3 | 20200302 | PSW |  |  |  |  | Auto | [5 empty] | T01 | duong.nguyen | hieu.nguyen-trung | Yes | 291 | 291 | 291 | 8 | 10 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-02 | 2020-03-03 | OK | 100 | 100 | 100
4 | 20200302 | PSW |  |  |  |  | Auto | [5 empty] | T01 | chung.ly | hieu.nguyen-trung | Yes | 254 | 254 | 254 | 4.51 | 10 | Pending for OPL | 2020-03-02 | 2020-03-03 | 2020-03-02 | 2020-03-03 | NG | 100 | 100 | 95
5 | 20200302 | ASW |  |  |  |  | Auto | [5 empty] | T01 | thanh.nguyen-kim | hieu.nguyen-trung | Yes | 19 | 19 | 19 | 1.16 | 4 | Pending for OPL | 2020-03-02 | 2020-03-03 | 2020-03-03 | 2020-03-03 | NG | 95.6 | 96 | -
6 | 20200302 | PSW |  |  |  |  | Auto | [5 empty] | T02 | thanh.nguyen-kim | hieu.nguyen-trung | Yes | 478 | 478 | 478 | 8.49 | 14 | Ready for PLC | 2020-03-02 | 2020-03-04 | 2020-03-02 | 2020-03-04 | NG | 99 | 99 | 100
7 | 20200302 | PSW |  |  |  |  | Auto | [5 empty] | T02 | loc.do-phu | hieu.nguyen-trung | Yes | 286 | 286 | 286 | 5.08 | 1 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-03 | 2020-03-02 | OK | 100 | 100 | 100
8 | 20200302 | PSW |  |  |  |  | Auto | [5 empty] | T02 | chung.ly | hieu.nguyen-trung | Yes | 110 | 110 | 110 | 1.95 | 4 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-04 | 2020-03-04 | OK | 100 | 100 | 100
9 | 20200302 | PSW |  |  |  |  | Auto | [5 empty] | T03 | loc.do-phu | hieu.nguyen-trung | Yes | 251 | 294 | 294 | 5.22 | 6.5 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-03 | 2020-03-03 | OK | 100 | 100 | 100
10 | 20200302 | PSW |  |  |  |  | Auto | [5 empty] | T03 | loc.do-phu | hieu.nguyen-trung | Yes | 101 | 101 | 101 | 1.79 | 1.5 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-04 | 2020-03-04 | OK | 100 | 100 | 100
11 | 20200302 | PSW |  |  |  |  | Auto | [5 empty] | T03 | duong.nguyen |  |  | 90 | 90 | 90 | 1.6 | 2 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-04 | 2020-03-04 | NG | 86 | 83 | 100
12 | 20200302 | PSW |  |  |  |  | Auto | [5 empty] | T03 | loc.do-phu | hieu.nguyen-trung | Yes | 101 | 183 | 183 | 3.25 | 3 | Ready for review | 2020-03-02 | 2020-03-04 | 2020-03-04 | 2020-03-04 | OK | 100 | 100 | 100
13 | 20200303 | PSW |  |  |  |  | Auto | [5 empty] | T01 | chung.ly |  |  | 828 | 828 |  | 14.72 | 16 | Ready for review | 2020-03-02 | 2020-03-09 | 2020-03-04 | 2020-03-06 | NG | 100 | 100 | 98
14 | 20200303 | PSW |  |  |  |  | Auto | [5 empty] | T01 | loc.do-phu |  |  | 371 | 371 |  | 6.59 | 3 | Ready for review | 2020-03-02 | 2020-03-09 | 2020-03-05 | 2020-03-05 | OK | 100 | 100 | 100
15 | 20200303 | PSW |  |  |  |  | Auto | [5 empty] | T01 | loc.do-phu |  |  | 254 | 254 | 254 | 4.51 | 2 | Ready for review | 2020-03-02 | 2020-03-09 | 2020-03-05 | 2020-03-05 | OK | 100 | 100 | 100
16 | 20200303 | PSW |  |  |  |  | Auto | [5 empty] | T01 | thanh.nguyen-kim |  |  | 395 | 395 | 395 | 7.02 | 2 | Ready for review | 2020-03-02 | 2020-03-09 | 2020-03-05 | 2020-03-05 | OK | 100 | 100 | 100
17 | 20200303 | PSW |  |  |  |  | Auto | [5 empty] | T01 | thanh.nguyen-kim |  |  | 395 | 395 | 395 | 7.02 | 3 | Ready for review | 2020-03-02 | 2020-03-09 | 2020-03-05 | 2020-03-05 | OK | 100 | 100 | 100
18 | 20200306 | PSW |  |  |  |  | Manual | [6 empty] | duong.nguyen | duong.nguyen | Yes | 96 | 96 | 96 | 1.7 | 1.5 | Ready for delivery |  | 2020-03-06 | 2020-03-06 | 2020-03-06 | NG | 97 | 95 | 92
19 | 20200306 | PSW |  |  |  |  | Manual | [6 empty] | loc.do-phu | duong.nguyen | Yes | 28 | 28 | 28 | 0.49 | 1 | Ready for delivery |  | 2020-03-06 | 2020-03-06 | 2020-03-06 | OK | 100 | 100 | 100
20 | 20200306 | PSW |  |  |  |  | Manual | [6 empty] | loc.do-phu | duong.nguyen | Yes | 36 | 36 | 36 | 0.64 | 1 | Ready for delivery |  | 2020-03-06 | 2020-03-06 | 2020-03-06 | OK | 100 | 100 | 100
21 | 20200306 | PSW |  |  |  |  | Manual | [6 empty] | chung.ly | duong.nguyen | Yes | 80 | 80 | 80 | 1.42 | 2 | Ready for delivery |  | 2020-03-06 | 2020-03-06 | 2020-03-06 | NG | 100 | 100 | 75
22 | 20200306 | PSW |  |  |  |  | Manual | [6 empty] | loc.do-phu | duong.nguyen | Yes | 33 | 33 | 33 | 0.58 | 1 | Ready for delivery |  | 2020-03-06 | 2020-03-06 | 2020-03-06 | OK | 100 | 100 | 100
23 | 20200306 | PSW |  |  |  |  | Manual | [6 empty] | thanh.nguyen-kim | duong.nguyen | Yes | 212 | 212 | 212 | 3.76 | 2 | Ready for delivery |  | 2020-03-06 | 2020-03-06 | 2020-03-06 | OK | 100 | 100 | 100
24 | 20200303 | ASW |  |  |  |  | Auto | [6 empty] | duong.nguyen |  |  | 50 | 50 | 50 | 3.07 | 3 | Ready for review | 2020-03-02 | 2020-03-09 | 2020-03-05 | 2020-03-06
25 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | duong.nguyen |  |  | 77 | 77 | 77 | 1.36 | 1 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
26 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | duong.nguyen |  |  | 44 | 44 |  | 0.78 |  | N/A |  | 2020-03-11
27 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | duong.nguyen |  |  | 210 | 210 | 210 | 3.73 | 2 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | OK | 100 | 100 | 100
28 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | duong.nguyen |  |  | 622 | 622 | 622 | 11.05 | 8 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | OK | 100 | 100 | 100
29 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | chung.ly |  |  | 97 | 97 |  | 1.72 | 1 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | OK | 100 | 100 | 100
30 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | chung.ly |  |  | 100 | 100 |  | 1.77 | 0.75 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | OK | 100 | 100 | 100
31 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | chung.ly |  |  | 8 | 8 |  | 0.14 | 0.2 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 |  | - | - | -
32 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | chung.ly |  |  | 148 | 148 |  | 2.63 | 1 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | OK | 100 | 100 | 100
33 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | thanh.nguyen-kim |  |  | 17 | 17 | 17 | 0.3 | 0.5 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
34 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | thanh.nguyen-kim |  |  | 18 | 18 | 18 | 0.32 | 0.5 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
35 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | loc.do-phu |  |  | 129 | 129 | 129 | 2.29 | 3 | Ready for review |  | 2020-03-11 | 2020-03-05 | 2020-03-05 | OK | 100 | 100 | 100
36 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | loc.do-phu |  |  | 164 | 196 | 196 | 3.48 | 4 | Ready for review |  | 2020-03-11 | 2020-03-06 | 2020-03-06 | OK | 100 | 100 | 100
37 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | loc.do-phu |  |  | 104 | 104 | 104 | 1.84 | 1 | Ready for review |  | 2020-03-11 | 2020-03-06 | 2020-03-10 | NG | 97 | 95 | 100
38 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | loc.do-phu |  |  | 154 | 154 | 154 | 2.73 | 2 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | NG | 98 | 96 | 100
39 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | loc.do-phu |  |  | 167 | 167 | 167 | 2.96 | 2 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
40 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | loc.do-phu |  |  | 147 | 147 | 147 | 2.61 | 1 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
41 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | loc.do-phu |  |  | 254 | 254 | 254 | 4.51 | 3 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
42 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | chung.ly |  |  | 193 | 193 |  | 3.43 | 2 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | NG | 100 | 100 | 91
43 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | chung.ly |  |  | 204 | 204 |  | 3.62 | 3 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
44 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | chung.ly |  |  | 194 | 194 |  | 3.44 | 1 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
45 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | chung.ly |  |  | 141 | 141 |  | 2.5 | 1 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | NG | 98 | 95 | 100
46 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | thanh.nguyen-kim |  |  | 190 | 190 | 190 | 3.37 | 4 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | NG | 66 | 100 | 100
47 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | thanh.nguyen-kim |  |  | 107 | 107 | 107 | 1.9 | 1 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | NG | 99 | 96 | 100
48 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | thanh.nguyen-kim |  |  | 269 | 269 | 269 | 4.78 | 3 | Pending for OPL |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | NG | 99 | 97 | 100
49 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | chung.ly |  |  | 70 | 70 |  | 1.24 | 0.2 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
50 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | thanh.nguyen-kim |  |  | 204 | 204 | 204 | 3.62 | 3 | Ready for review | 2020-03-05 | 2020-03-11 | 2020-03-05 | 2020-03-06 | OK | 100 | 100 | 100
51 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | thanh.nguyen-kim |  |  | 185 | 185 | 185 | 3.28 | 3 | Ready for review | 2020-03-05 | 2020-03-11 | 2020-03-05 | 2020-03-06 | OK | 100 | 100 | 100
52 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | duong.nguyen |  |  | 68 | 68 | 68 | 1.2 | 1 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
53 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | duong.nguyen |  |  | 150 | 150 | 150 | 2.66 | 2 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
54 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | thanh.nguyen-kim |  |  | 25 | 25 | 25 | 0.44 | 0.2 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
55 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | chung.ly |  |  | 487 | 487 |  | 8.65 | 2.4 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | OK | 100 | 100 | 100
56 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | thanh.nguyen-kim |  |  | 110 | 110 | 110 | 1.95 | 2 | Ready for review | 2020-03-05 | 2020-03-11 | 2020-03-05 | 2020-03-05 | OK | 100 | 100 | 100
57 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | chung.ly |  |  | 167 | 167 |  | 2.96 | 1 | Ready for review |  | 2020-03-11 | 2020-03-09 | 2020-03-09 | OK | 100 | 100 | 100
58 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | thanh.nguyen-kim |  |  | 42 | 42 | 42 | 0.74 | 0.2 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
59 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | thanh.nguyen-kim |  |  | 40 | 40 | 40 | 0.71 | 0.3 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
60 | 20200303 | PSW |  |  |  |  | Manual | [9 empty] | 44 | 44 |  | 0.78 |  | N/A |  | 2020-03-11
61 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | thanh.nguyen-kim |  |  | 29 | 29 | 29 | 0.51 | 0.5 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
62 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | thanh.nguyen-kim |  |  | 110 | 110 | 110 | 1.95 | 1.5 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
63 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | thanh.nguyen-kim |  |  | 42 | 42 | 42 | 0.74 | 0.5 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
64 | 20200303 | PSW |  |  |  |  | Manual | [6 empty] | thanh.nguyen-kim |  |  | 44 | 44 | 44 | 0.78 | 0.7 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
65 | 20200305 | PSW |  |  |  |  | Auto | [6 empty] | thanh.nguyen-kim |  |  | 117 | 117 | 117 | 2.08 | 3 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
66 | 20200305 | PSW |  |  |  |  | Auto | [6 empty] | thanh.nguyen-kim |  |  | 55 | 122 | 122 | 2.16 | 1.5 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
67 | 20200305 | PSW |  |  |  |  | Auto | [6 empty] | thanh.nguyen-kim |  |  | 60 | 60 | 60 | 1.06 | 0.5 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
68 | 20200305 | PSW |  |  |  |  | Auto | [6 empty] | thanh.nguyen-kim |  |  | 30 | 30 | 30 | 0.53 | 0.2 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
69 | 20200305 | PSW |  |  |  |  | Auto | [6 empty] | thanh.nguyen-kim |  |  | 34 | 34 | 34 | 0.6 | 0.3 | Ready for review |  | 2020-03-11 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
70 | 20200305 | PSW |  |  |  |  | Auto | [6 empty] | chung.ly |  |  | 357 | 357 |  | 6.34 | 1 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
71 | 20200305 | PSW |  |  |  |  | Auto | [6 empty] | chung.ly |  |  | 431 | 431 |  | 7.66 | 1 | Ready for review |  | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
72 | 20200304 | PSW |  |  |  |  | Manual | [6 empty] | chung.ly |  |  | 1993 | 1993 |  | 35.43 | 3 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 | NG | 100 | 100 | 100
73 | 20200304 | PSW |  |  |  |  | Manual | [6 empty] | chung.ly |  |  | 489 | 489 |  | 8.69 | 2 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 | NG | 99 | 98 | 100
74 | 20200304 | PSW |  |  |  |  | Manual | [6 empty] | thanh.nguyen-kim |  |  | 593 | 587 |  | 10.43 |  | Ongoing |  | 2020-03-12 | 2020-03-11
75 | 20200304 | PSW |  |  |  |  | Manual | [6 empty] | duong.nguyen |  |  | 165 |  |  |  |  | N/A |  | 2020-03-12
76 | 20200304 | PSW |  |  |  |  | Manual | [6 empty] | chung.ly |  |  | 8 | 8 | 8 |  | 0.2 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
77 | 20200304 | PSW |  |  |  |  | Manual | [6 empty] | chung.ly |  |  | 71 | 71 |  |  | 0.5 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
78 | 20200304 | PSW |  |  |  |  | Manual | [6 empty] | chung.ly |  |  | 55 |  |  |  | 0.5 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
79 | 20200304 | PSW |  |  |  |  | Manual | [6 empty] | chung.ly |  |  | 64 |  |  |  | 0.5 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
80 | 20200304 | PSW |  |  |  |  | Manual | [6 empty] | chung.ly |  |  | 69 | 69 |  |  | 0.2 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
81 | 20200304 | PSW |  |  |  |  | Manual | [6 empty] | chung.ly |  |  | 5 |  |  |  | 0.1 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 |  | - | - | -
82 | 20200304 | PSW |  |  |  |  | Manual | [6 empty] | chung.ly |  |  | 3 | 3 | 3 |  | 0.2 | Ready for review |  | 2020-03-12 | 2020-03-11 | 2020-03-11 | OK | 100 | 100 | 100
83 | 20200304 | PSW |  |  |  |  | Manual | [6 empty] | duong.nguyen |  |  | 220 |  |  |  |  | N/A |  | 2020-03-12
84 | 20200304 | PSW |  |  |  |  | Manual | [9 empty] | 4 |  |  |  |  | N/A |  | 2020-03-12
85 | 20200304 | PSW |  |  |  |  | Manual | [9 empty] | 12 |  |  |  |  | N/A |  | 2020-03-12
86 | 20200304 | PSW |  |  |  |  | Manual | [9 empty] | 37 |  |  |  |  | N/A |  | 2020-03-12
87 | 20200309 | PSW |  |  |  |  | Auto | [9 empty] | 67
88 | 20200309 | PSW |  |  |  |  | Auto | [6 empty] | thanh.nguyen-kim |  |  | 130
89 | 20200309 | PSW |  |  |  |  | Auto | [6 empty] | loc.do-phu |  |  | 1703 | 1703 |  |  | 8
90 | 20200309 | PSW |  |  |  |  | Auto | [6 empty] | thanh.nguyen-kim |  |  | 144
91 | 20200309 | PSW |  |  |  |  | Auto | [9 empty] | 111
92 | 20200309 | PSW |  |  |  |  | Auto | [9 empty] | 12
93 | 20200309 | PSW |  |  |  |  | Auto | [6 empty] | thanh.nguyen-kim |  |  | 191
94 | 20200309 | PSW |  |  |  |  | Auto | [9 empty] | 21
95 | 20200309 | PSW |  |  |  |  | Auto | [9 empty] | 25
96 | 20200309 | PSW |  |  |  |  | Auto | [6 empty] | thanh.nguyen-kim |  |  | 151
97 | 20200309 | PSW |  |  |  |  | Auto | [6 empty] | duong.nguyen |  |  | 178
98 | 20200309 | PSW |  |  |  |  | Auto | [6 empty] | thanh.nguyen-kim |  |  | 280
99 | 20200309 | PSW |  |  |  |  | Auto | [6 empty] | duong.nguyen |  |  | 259
100 | 20200309 | PSW |  |  |  |  | Auto | [9 empty] | 35
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
Table KPI ASW
No | Tester | Total Loc Assigned | Total LOC Complete | Total Day | KPI/days | Status (%)
1 | hieu.nguyen-trung | 0 | 0 | 0 | N/A | N/A
2 | hau.nguyen-tai | 0 | 0 | 0 | N/A | N/A
3 | bang.nguyen-duy | 0 | 0 | 0 | N/A | N/A
4 | dac.luu-cong | 0 | 0 | 0 | N/A | N/A
5 | duong.nguyen | 50 | 50 | 0.375 | 133.3333 | 100%
6 | loc.do-phu | 0 | 0 | 0 | N/A | N/A
7 | thanh.nguyen-kim | 19 | 19 | 0.5 | 38 | 100%
8 | chung.ly | 0 | 0 | 0 | N/A | N/A
Table KPI PSW
No | Tester | Total Loc Assigned | Total LOC Complete | Total Day | KPI/days | Status (%)
1 | hieu.nguyen-trung | 0 | 0 | 0 | N/A | N/A
2 | hau.nguyen-tai | 0 | 0 | 0 | N/A | N/A
3 | bang.nguyen-duy | 0 | 0 | 0 | N/A | N/A
4 | dac.luu-cong | 0 | 0 | 0 | N/A | N/A
5 | duong.nguyen | 1761 | 1717 | 3.9375 | 436.0635 | 97.5%
6 | loc.do-phu | 4797 | 4797 | 6.25 | 767.52 | 100%
7 | thanh.nguyen-kim | 3862 | 3275 | 5.925 | 552.7426 | 84.8%
8 | chung.ly | 6502 | 6502 | 6.8438 | 950.0639 | 100%
Note on A29: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): Purple must be complete before 11-03
Note on I29: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): Must be run Tool Auto Comment to generate header and add cmt in section "Test Goal"
Note on K71: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): \\hc-ut40745c\Ban_Vien_external\DB\05-march
Note on A76: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): Yellow must be complete before 12-03
Note on K76: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): \\hc-ut40745c\Ban_Vien_external\DB\04-march
Note on I78: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): Must be use "Auto Comment"
Note on A91: EXTERNAL Nguyen Tuan Duong (Ban Vien, RBVH/EPS45): Orange must be complete before 13_Mar

## Table
KPI Table
No\Type | ASW | PSW
1 | 130 | 450
Table Type of Testing
No | Type | Tool | Detail Output
1 | ASW | ATT | 1. Test Design (.xls) 2. Plot File (.plt) 3. ATT project 4. Coverage Log
2 | PSW | Cantata | 1. TPA file (.tpa) 2. test report (.html) 3. test report (.xml) 4. test summary (.html) 5. File Coverage Fail Reason (.xls)
Table Tester
No | Member
1 | hieu.nguyen-trung
2 | hau.nguyen-tai
3 | bang.nguyen-duy
4 | dac.luu-cong
5 | duong.nguyen
6 | loc.do-phu
7 | thanh.nguyen-kim
8 | chung.ly
Status Table
No | Status
1 | N/A |  | COEM process: test-->review test----(feedback no finding)-->generate WT----(review WT no finding)---> done task Tức là bên anh gửi UT output cho internal => Có OPL có bug => Internal review OK => Làm walkthrough => Sau đó internal review Walkthrough => Send email cho External confirm OK => Mark Done
2 | Ongoing
3 | Ready for review
4 | Ready for delivery
5 | Ready for PLC
6 | Pending for OPL
7 | Complete & Closed

## Template_Weekly_Report
Date | 2020-02-03
Total Days | 20
1. Completed ELOCs of the team from the beginning of Month (Mar) till Now:
|  | # | Types | Assigned ELOCs | Completed ELOCs | Status (%) (Completed/Assigned)
|  | 1 | PSW | ??? | ??? | ???
|  | 2 | ASW | ??? | ??? | ???
2. Completed ELOCs of each member from the beginning of Month (Mar) till Now:
|  | # | External Name | PSW ELOCs | ASW ELOCs
|  | 1 | hieu.nguyen-trung | ??? | ???
|  | 2 | duong.nguyen-tuan | ??? | ???
3. Risks/ Pending Issues:
|  | # | Risks/ Issues
1
2
4. Found Defects/ OPLs in Month (Mar):
|  | # | Defects / OPLs
1
2
5. Leave Plan (Mar):
|  | # | External Name | Num of Day | Detail
|  | 1 | hieu.nguyen-trung | ??? | ???
|  | 2 | duong.nguyen-tuan | ??? | ???
Note:
Productivity of each Member per Day
PSW: 450 ELOCs
ASW: 150 ELOCs
Total Productivity per Month
PSW: 450x4x20 = 36,000 ELOCs
ASW: 130x4x20 = 10,400 ELOCs

## Check_List
Location
| + Location Internal Project: | \\hc-ut40346c\NHI5HC\hieunguyen\0000_Project
| + Location Internal Your Output: | \\hc-ut40346c\NHI5HC\hieunguyen\0000_Project\001_Prj\01_COEM\01_Output_Package
Please ensure your push correct the Package name with the TaskGroup
| + Location Internal Your Release Output: | \\hc-ut40346c\NHI5HC\hieunguyen\0000_Project\001_Prj\01_COEM\02_Release_Package
| + Location for delivery to internal team: | \\hc-ut40745c\Ban_Vien_external\Release\Gen_9.3