## JOEM_Package_20200305
No | Package | Type | Project | ComponentName | TaskID | ItemName | Type of Comment | BB | Database | ItemRevision | Owner Contact | Task Jira | TaskGroup | Tester | PeerReviewer | Status Review | ELOC Assigned | ELOC Recheck With Tool | LOC Complete | Estimation base TOOL | Actual hour | Status | Planned Start | Planned End | Start | End | Status Result | C0 | C1 | MCDC | Reason | Remark
1 | 20200305 | ASW | [10 empty] | T500 | hieu.nguyen-trung |  |  | 38 | 37.2937 | 37.2937 | 2.295 | 2 | Ready for PLC | 2020-03-06 | 2020-03-11 | 2020-03-06 | 2020-03-06 | OK | 100 | 100 | 100
2 | 20200305 | ASW | [10 empty] | T500 | hieu.nguyen-trung |  |  | 26 | 20.7188 | 20.7188 | 1.275 | 1 | Ready for PLC | 2020-03-06 | 2020-03-11 | 2020-03-06 | 2020-03-09 | OK | 100 | 100 | 100
3 | 20200305 | ASW | [10 empty] | T500 | hieu.nguyen-trung |  |  | 35 | 26.2437 | 26.2437 | 1.615 | 1 | Ready for PLC | 2020-03-06 | 2020-03-11 | 2020-03-06 | 2020-03-09 | OK | 100 | 100 | 100
4 | 20200305 | ASW | [10 empty] | T500 | hieu.nguyen-trung |  |  | 55 | 37.2937 | 37.2937 | 2.295 | 3 | Ready for PLC | 2020-03-06 | 2020-03-11 | 2020-03-06 | 2020-03-11 | OK | 100 | 100 | 100
5 | 20200305 | ASW | [10 empty] | T500 | hieu.nguyen-trung |  |  | 150 | 125.6937 | 125.6937 | 7.735 | 8 | Ready for PLC | 2020-03-06 | 2020-03-11 | 2020-03-06 | 2020-03-10 | OK | 96.5 | 96.6 | 100
6 | 20200305 | ASW | [10 empty] | T500 | hieu.nguyen-trung |  |  | 195 | 169.8938 |  | 10.455 |  | N/A | 2020-03-06 | 2020-03-11 | 2020-03-10
7 | 20200305 | ASW | [10 empty] | T500 | hieu.nguyen-trung |  |  | 99 | 59.3937 |  | 3.655 |  | Ongoing | 2020-03-06 | 2020-03-11 | 2020-03-06
8 | 20200305 | ASW | [10 empty] | T500 | hieu.nguyen-trung |  |  | 49 | 42.8187 | 42.8187 | 2.635 | 5 |  | 2020-03-06 | 2020-03-11 | 2020-03-06
9 | 20200305 | ASW | [10 empty] | T500 | hieu.nguyen-trung |  |  | 62 | 26.2437 |  | 1.615 |  |  | 2020-03-06 | 2020-03-11 | 2020-03-06
10 | 20200305 | ASW | [10 empty] | T500 | hieu.nguyen-trung |  |  | 70 | 48.3438 |  | 2.975 |  |  | 2020-03-06 | 2020-03-11 | 2020-03-06
11 | 20200305 | ASW | [10 empty] | T500 | hieu.nguyen-trung |  |  | 20 | 26.2437 |  | 1.615 |  |  | 2020-03-06 | 2020-03-11 | 2020-03-06
12 | 20200305 | ASW | [10 empty] | T501 | hau.nguyen-tai |  |  | 317 | 147.7937 | 40 | 9.095 | 4 | Ongoing | 2020-03-06 | 2020-03-11 | 2020-03-06
13 | 20200305 | ASW | [10 empty] | T501 | hau.nguyen-tai |  |  | 93 | 48.3438 | 48.3438 | 2.975 | 4 | Ready for review | 2020-03-06 | 2020-03-11 | 2020-03-11 | 2020-03-11 | NG | 91.7 | 91.7 | 83.3
14 | 20200305 | ASW | [10 empty] | T501 | hau.nguyen-tai |  |  | 52 | 31.7687 | 31.7687 | 1.955 | 4 | Ready for review | 2020-03-06 | 2020-03-11 | 2020-03-06 | 2020-03-06 | NG | 100 | 100 | 93.8% - 50%
15 | 20200305 | ASW | [10 empty] | T501 | hau.nguyen-tai |  |  | 45 | 26.2437 | 26.2437 | 1.615 | 3 | Ready for review | 2020-03-06 | 2020-03-11 | 2020-03-09 | 2020-03-09 | OK | 100 | 100 | 100
16 | 20200305 | ASW | [10 empty] | T501 | hau.nguyen-tai |  |  | 38 | 26.2437 | 26.2437 | 1.615 | 3 | Ready for review | 2020-03-06 | 2020-03-11 | 2020-03-06 | 2020-03-06 | OK | 100 | 100 | 100
17 | 20200305 | ASW | [10 empty] | T501 | hau.nguyen-tai |  |  | 80 | 125.6937 | 100 | 7.735 | 4 | Ongoing | 2020-03-06 | 2020-03-11 | 2020-03-06
18 | 20200305 | ASW | [10 empty] | T501 | hau.nguyen-tai |  |  | 60 | 31.7687 | 31.7687 | 1.955 | 2 | Ready for review | 2020-03-06 | 2020-03-11 | 2020-03-09 | 2020-03-09 | OK | 96 | 96 | 95.1
19 | 20200305 | ASW | [10 empty] | T501 | hau.nguyen-tai |  |  | 103 | 48.3438 |  | 2.975 |  |  | 2020-03-06 | 2020-03-11 | 2020-03-06
20 | 20200305 | ASW | [10 empty] | T501 | hau.nguyen-tai |  |  | 45 | 26.2437 | 26.2437 | 1.615 | 2 | Ready for review | 2020-03-06 | 2020-03-11 | 2020-03-09 | 2020-03-09 | NG | 100 | 100 | 100
21 | 20200305 | ASW | [10 empty] | T501 | hau.nguyen-tai |  |  | 54 | 59.3937 | 59.3937 | 3.655 | 2 | Ready for review | 2020-03-06 | 2020-03-11 | 2020-03-11 | 2020-03-11 | NG | 100 | 100 | 92.3
22 | 20200305 | ASW | [10 empty] | T501 | hau.nguyen-tai |  |  | 50 | 37.2937 | 37.2937 | 2.295 | 2 | Ready for review | 2020-03-06 | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | 100
23 | 20200305 | ASW | [10 empty] | T501 | hau.nguyen-tai |  |  | 39 | 26.2437 | 26.2437 | 1.615 | 2 | Ready for review | 2020-03-06 | 2020-03-11 | 2020-03-10 | 2020-03-10 | OK | 100 | 100 | NA
24 | 20200305 | ASW | [10 empty] | T502 | dac.luu-cong |  |  | 531 | 42.8187 | 42.8187 | 2.635 | 3 | Ready for review | 2020-03-06 | 2020-03-11 | 2020-03-06 | 2020-03-11 | OK | 100 | 100 | 0
25 | 20200305 | ASW | [10 empty] | T502 | dac.luu-cong |  |  | 36 | 20.7188 | 20.7188 | 1.275 | 2 | Ready for review | 2020-03-06 | 2020-03-11 | 2020-03-06 | 2020-03-06 | OK | 100 | 100 | 100
26 | 20200305 | ASW | [10 empty] | T502 | dac.luu-cong |  |  | 10 | 20.7188 | 20.7188 | 1.275 | 2 | Ready for review | 2020-03-06 | 2020-03-11 | 2020-03-06 | 2020-03-11 | OK | 100 | 100 | 0
27 | 20200305 | ASW | [10 empty] | T502 | dac.luu-cong |  |  | 36 | 20.7188 | 20.7188 | 1.275 | 2 | Ready for review | 2020-03-06 | 2020-03-11 | 2020-03-06 | 2020-03-11 | OK | 100 | 100 | 0
28 | 20200305 | ASW | [10 empty] | T502 | dac.luu-cong |  |  | 36 | 20.7188 | 20.7188 | 1.275 | 2 | Ready for review | 2020-03-06 | 2020-03-11 | 2020-03-06 | 2020-03-11 | OK | 100 | 100 | 0
29 | 20200305 | ASW | [10 empty] | T502 | dac.luu-cong |  |  | 10 | 20.7188 | 20.7188 | 1.275 | 1 | Ready for review | 2020-03-06 | 2020-03-11 | 2020-03-06 | 2020-03-11 | OK | 100 | 100 | 0
30 | 20200305 | ASW | [10 empty] | T502 | dac.luu-cong |  |  | 61 | 26.2437 | 26.2437 | 1.615 | 2 | Ready for review | 2020-03-06 | 2020-03-11 | 2020-03-06 | 2020-03-11 | OK | 100 | 100 | 0
31 | 20200305 | ASW | [10 empty] | T502 | dac.luu-cong |  |  | 89 | 125.6937 | 125.6937 | 7.735 | 8 | Ready for review | 2020-03-06 | 2020-03-11 | 2020-03-06 | 2020-03-11 | NG | 100 | 100 | 94.1
32 | 20200305 | ASW | [10 empty] | T502 | dac.luu-cong |  |  | 67 | 26.2437 |  | 1.615 |  |  | 2020-03-06 | 2020-03-11 | 2020-03-06
33 | 20200305 | ASW | [10 empty] | T502 | dac.luu-cong |  |  | 51 | 42.8187 | 42.8187 | 2.635 | 3 | Ready for review | 2020-03-06 | 2020-03-11 | 2020-03-06 | 2020-03-09 | OK | 100 | 100 | 100
34 | 20200305 | ASW | [10 empty] | T502 | dac.luu-cong |  |  | 71 | 53.8688 | 53.8688 | 3.315 | 4 | Ready for review | 2020-03-06 | 2020-03-11 | 2020-03-06 | 2020-03-09 | NG | 100 | 100 | 100
35 | 20200305 | ASW | [10 empty] | T502 | dac.luu-cong |  |  | 58 | 37.2937 |  | 2.295 |  |  | 2020-03-06 | 2020-03-11 | 2020-03-06
36 | 20200305 | ASW | [10 empty] | T502 | dac.luu-cong |  |  | 47 |  |  | 1.615 |  |  | 2020-03-06 | 2020-03-11 | 2020-03-06
37 | 20200305 | ASW | [10 empty] | T502 | dac.luu-cong |  |  | 32 | 31.7687 |  | 1.955 |  |  | 2020-03-06 | 2020-03-11 | 2020-03-06
38 | 20200305 | ASW | [10 empty] | T502 | dac.luu-cong |  |  | 73 | 42.8187 | 42.8187 | 2.635 | 3 | Ready for review | 2020-03-06 | 2020-03-11 | 2020-03-06 | 2020-03-06 | OK | 100 | 100 | 100
39 | 20200306 | ASW | [10 empty] | T02 | hieu.nguyen-trung |  | 26.2437 | 13 | 26 | 26 | 1.6 | 3 | Complete & Closed | 2020-03-06 | 2020-03-09 | 2020-03-06 | 2020-03-06 | NG | 84.6 | 84.6 | -
40 | 20200306 | ASW | [10 empty] | T02 | hieu.nguyen-trung |  |  | 52 | 78 | 78 | 4.8 | 5 | Complete & Closed | 2020-03-06 | 2020-03-09 | 2020-03-06 | 2020-03-06 | NG | 88.9 | 89.4 | 88.9
41 | 20200306 | ASW | [10 empty] | T02 | hieu.nguyen-trung |  |  | 28 | 39 | 39 | 2.4 | 4 | Complete & Closed | 2020-03-06 | 2020-03-09 | 2020-03-09 | 2020-03-09 | OK | 100 | 100 | 100
-
-
-
-
-
-
-
-
-
-
-
-
-
-
Table KPI ASW
No | Tester | Total Loc Assigned | Total LOC Complete | Total Day | KPI/days | Status (%)
1 | hieu.nguyen-trung | 763.1812 | 433.0625 | 4 | 108.2656 | 56.74%
2 | hau.nguyen-tai | 635.375 | 313.5437 | 3 | 104.5146 | 49.35%
3 | bang.nguyen-duy | 0 | 0 | 0 | N/A | N/A
4 | dac.luu-cong | 533.1625 | 437.8563 | 4 | 109.4641 | 82.12%
5 | duong.nguyen | 0 | 0 | 0 | N/A | N/A
6 | loc.do-phu | 0 | 0 | 0 | N/A | N/A
7 | thanh.nguyen-kim | 0 | 0 | 0 | N/A | N/A
8 | chung.ly | 0 | 0 | 0 | N/A | N/A
Table KPI PSW
No | Tester | Total Loc Assigned | Total LOC Complete | Total Day | KPI/days | Status (%)
1 | hieu.nguyen-trung | 0 | 0 | 0 | N/A | N/A
2 | hau.nguyen-tai | 0 | 0 | 0 | N/A | N/A
3 | bang.nguyen-duy | 0 | 0 | 0 | N/A | N/A
4 | dac.luu-cong | 0 | 0 | 0 | N/A | N/A
5 | duong.nguyen | 0 | 0 | 0 | N/A | N/A
6 | loc.do-phu | 0 | 0 | 0 | N/A | N/A
7 | thanh.nguyen-kim | 0 | 0 | 0 | N/A | N/A
8 | chung.ly | 0 | 0 | 0 | N/A | N/A

## Table
KPI Table
No\Type | ASW | PSW
1 | 130 | 450
Table Type of Testing
No | Type | Tool | Detail Output
1 | ASW | ATT | 1. Test Design (.xls) 2. Plot File (.plt) 3. ATT project 4. Coverage Log
2 | PSW | Cantata | 1. TPA file (.tpa) 2. test report (.html) 3. test report (.xml) 4. test summary (.html) 5. File Coverage Fail Reason (.xls)
Table Tester
No | Member
1 | hieu.nguyen-trung
2 | hau.nguyen-tai
3 | bang.nguyen-duy
4 | dac.luu-cong
5 | duong.nguyen
6 | loc.do-phu
7 | thanh.nguyen-kim
8 | chung.ly
Status Table
No | Status
1 | N/A |  | COEM process: test-->review test----(feedback no finding)-->generate WT----(review WT no finding)---> done task Tức là bên anh gửi UT output cho internal => Có OPL có bug => Internal review OK => Làm walkthrough => Sau đó internal review Walkthrough => Send email cho External confirm OK => Mark Done
2 | Ongoing
3 | Ready for review
4 | Ready for delivery
5 | Ready for PLC
6 | Pending for OPL
7 | Complete & Closed

## Template_Weekly_Report
Date | 2020-02-03
Total Days | 20
1. Completed ELOCs of the team from the beginning of Month (Mar) till Now:
|  | # | Types | Assigned ELOCs | Completed ELOCs | Status (%) (Completed/Assigned)
|  | 1 | PSW | ??? | ??? | ???
|  | 2 | ASW | ??? | ??? | ???
2. Completed ELOCs of each member from the beginning of Month (Mar) till Now:
|  | # | External Name | PSW ELOCs | ASW ELOCs
|  | 1 | hieu.nguyen-trung | ??? | ???
|  | 2 | duong.nguyen-tuan | ??? | ???
3. Risks/ Pending Issues:
|  | # | Risks/ Issues
1
2
4. Found Defects/ OPLs in Month (Mar):
|  | # | Defects / OPLs
1
2
5. Leave Plan (Mar):
|  | # | External Name | Num of Day | Detail
|  | 1 | hieu.nguyen-trung | ??? | ???
|  | 2 | duong.nguyen-tuan | ??? | ???
Note:
Productivity of each Member per Day
PSW: 450 ELOCs
ASW: 130 ELOCs
Total Productivity per Month
PSW: 450x4x20 = 36,000 ELOCs
ASW: 130x4x20 = 10,400 ELOCs

## Check_List
Location
| + Location Internal Project: | \\hc-ut40346c\NHI5HC\hieunguyen\0000_Project
| + Location Internal Your Output: | \\hc-ut40346c\NHI5HC\hieunguyen\0000_Project\001_Prj\01_COEM\01_Output_Package
Please ensure your push correct the Package name with the TaskGroup
| + Location Internal Your Release Output: | \\hc-ut40346c\NHI5HC\hieunguyen\0000_Project\001_Prj\01_COEM\02_Release_Package
| + Location for delivery to internal team: | \\hc-ut40745c\Ban_Vien_external\Release\Gen_9.3