## Summary
No | Type | File | TaskGroup | Tester | LOC | LOC Complete | Estimation hour | Actual hour | Status | Start | End | C0 | C1 | MCDC | Reason
1 | ASW | DiagramA_1 | T01 | hieu.nguyen-trung | 103 | 80 | 6.33 | 8 | Ongoing | 2020-02-24 | 2020-02-24 | 94 | 95 | 68
2 | ASW | DiagramA_2 | T02 | duong.nguyen-tuan | 141 | 70 | 8.67 | 9 | Ready for review | 2020-02-25 | 2020-02-25 | 98 | 91 | 67
3 | ASW | DiagramA_3 | T01 | hieu.nguyen-trung | 98 | 98 | 6.03 | 8 | Ready for review | 2020-02-26 | 2020-02-26 | 96 | 95 | 83
4 | ASW | DiagramA_4 | T02 | duong.nguyen-tuan | 74 | 74 | 4.55 | 5 | Ready for review | 2020-02-27 | 2020-02-27 | 93 | 95 | 75
5 | ASW | DiagramA_5 | T01 | hieu.nguyen-trung | 53 | 53 | 3.26 | 3 | Ready for review | 2020-02-28 | 2020-02-28 | 90 | 98 | 98
6 | ASW | DiagramA_6 | T02 | duong.nguyen-tuan | 80 | 80 | 4.92 | 4 | Ready for review | 2020-02-29 | 2020-02-29 | 98 | 100 | 82
7 | PSW | a_1.c_1 | T01 | hieu.nguyen-trung | 442 | 442 | 7.85 | 8 | Ready for review | 2020-03-01 | 2020-03-01 | 94 | 92 | 89
8 | PSW | a_1.c_2 | T02 | duong.nguyen-tuan | 441 | 441 | 7.84 | 7 | Ongoing | 2020-03-02 | 2020-03-02 | 91 | 92 | 80
9 | PSW | a_1.c_3 | T01 | hieu.nguyen-trung | 886 | 886 | 15.75 | 8 | Ready for review | 2020-03-03 | 2020-03-03 | 98 | 95 | 87
10 | PSW | a_1.c_4 | T02 | duong.nguyen-tuan | 338 | 338 | 6 | 10 | Ready for review | 2020-03-04 | 2020-03-04 | 91 | 95 | 52
11 | PSW | a_1.c_5 | T01 | hieu.nguyen-trung | 994 | 994 | 17.67 | 24 | Ready for review | 2020-03-05 | 2020-03-05 | 92 | 93 | 87
12 | PSW | a_1.c_6 | T02 | duong.nguyen-tuan | 629 | 629 | 11.18 | 10 | Ready for review | 2020-03-06 | 2020-03-06 | 93 | 96 | 95
Table KPI ASW
No | Tester | Total Loc Assigned | Total LOC Complete | Total Day | KPI/days | Status (%)
1 | hieu.nguyen-trung | 254 | 151 | 1.375 | 109.8182 | 59.45%
2 | duong.nguyen-tuan | 295 | 224 | 2.25 | 99.5556 | 75.93%
3
Table KPI PSW
No | Tester | Total Loc Assigned | Total LOC Complete | Total Day | KPI/days | Status (%)
1 | hieu.nguyen-trung | 2322 | 2322 | 5 | 464.4 | 100%
2 | duong.nguyen-tuan | 1408 | 967 | 2.5 | 386.8 | 68.68%
3

## Table
KPI Table
No\Type | ASW | PSW
1 | 130 | 450
Table Type of Testing
No | Type | Tool | Detail Output
1 | ASW | ATT | 1. Test Design (.xls) 2. Plot File (.plt) 3. ATT project 4. Coverage Log
2 | PSW | Cantata | 1. TPA file (.tpa) 2. test report (.html) 3. test report (.xml) 4. test summary (.html) 5. File Coverage Fail Reason (.xls)
Table Tester
No | Member
1 | hieu.nguyen-trung
2 | duong.nguyen-tuan
Status Table
No | Status
1 | N/A
2 | Ongoing
3 | Ready for review
4 | Ready for PLC

## Template_Weekly_Report
Date | 2020-02-03
Total Days | 20
| 1. Completed ELOCs of the team from the beginning of Month (Mar) till Now: | [5 empty] | 1. Completed ELOCs of the team from the beginning of Month (Mar) till Now:
|  | # | Types | Assigned ELOCs | Completed ELOCs | Status (%) (Completed/Assigned) |  | # | Types | Assigned ELOCs | Completed ELOCs | Status (%) (Completed/Assigned)
|  | 1 | PSW | 811 | 0 | 0 |  | 1 | PSW | 811 | 0 | 0
|  | 2 | ASW | 7416 | 3076 | 41.48 |  | 2 | ASW | 7416 | 3076 | 41.48
|  | Already release package for project: PSA, TOY | [5 empty] | Already release package for project:
| 2. Completed ELOCs of each member from the beginning of Month (Mar) till Now: | [5 empty] | 2. Completed ELOCs of each member from the beginning of Month (Mar) till Now:
|  | # | External Name | PSW ELOCs | ASW ELOCs | Effort (days) (Tool) |  | # | External Name | PSW ELOCs | ASW ELOCs
|  | 1 | Nguyen Trung Hieu | 49 | 892 | 5.8706 |  | 1 | Nguyen Tuan Duong | 49 | 892
|  | 2 | Nguyen Tai Hau | 0 | 976 | 4.8875 |  | 2 | Do Phu Loc | 0 | 976
|  | 3 | Nguyen Duy Bang | 762 | 0 | 0 |  | 3 | Nguyen Kim Thanh | 762 | 0
|  | 4 | Luu Cong Dac | 0 | 1208 | 4.3031 |  | 4 | Ly Chung | 0 | 1208
| 3. Risks/ Pending Issues: | [5 empty] | 3. Risks/ Pending Issues:
|  | # | Risks/ Issues |  |  |  |  | # | Risks/ Issues
|  | 1 | Take time to do action item of review phase. |  |  |  |  | 1 | Delay for release package with planned 13_Mar due to fix all findings of package 11_Mar from Test coordinator of RBVH. Remain 102 ELOC for release package 13_Mar.
|  | 2 | Lacked 1 person, so we need to proceed task with 3 person |  |  |  |  | 2 | Progress to complete PSW task is dependent of complexity of class.
|  | 3 | [5 empty] | 3
|  | 4 | [5 empty] | 4
| 4. Found Defects/ OPLs in Month (Mar): | [5 empty] | 4. Found Defects/ OPLs in Month (Mar):
|  | # | Defects / OPLs |  |  |  |  | # | Defects / OPLs
|  | 1 | - |  |  |  |  | 1 | Duong: 1
|  | 2 | - |  |  |  |  | 2 | Loc: 1
|  | 3 | - |  |  |  |  | 3 | Thanh: 3
|  | 4 | - |  |  |  |  | 4 | Chung: 3
| 5. Leave Plan (Mar): | [5 empty] | 5. Leave Plan (Mar):
|  | # | External Name | Num of Day | Detail |  |  | # | External Name | Num of Day | Detail
|  | 1 | Nguyen Trung Hieu | - | - |  |  | 1 | Nguyen Tuan Duong | - | -
|  | 2 | Nguyen Tai Hau | - | - |  |  | 2 | Do Phu Loc | - | -
|  | 3 | Nguyen Duy Bang | - | - |  |  | 3 | Nguyen Kim Thanh | - | -
|  | 4 | Luu Cong Dac | - | - |  |  | 4 | Ly Chung | - | -
| Note: | [5 empty] | Note:
|  | Productivity of each Member per Day | [5 empty] | Productivity of each Member per Day
|  |  | PSW: 450 ELOCs | [5 empty] | PSW: 450 ELOCs
|  |  | ASW: 150 ELOCs | [5 empty] | ASW: 150 ELOCs
|  | Total Productivity per Month | [5 empty] | Total Productivity per Month
|  |  | PSW: 450x4x20 = 36,000 ELOCs | [5 empty] | PSW: 450x4x20 = 36,000 ELOCs
|  |  | ASW: 130x4x20 = 10,400 ELOCs | [5 empty] | ASW: 130x4x20 = 10,400 ELOCs